## Defect Log
Defect ID | Title | Module | Severity | Priority | Found Via | Found In | Description | Steps to Reproduce | Expected Result | Actual Result | Resolution | Status | Date Logged | Date Resolved
DEF-001 | Slips table missing IsPrinted/CreatedAt columns referenced elsewhere | Database Schema | Critical | Critical | Code Review | Review Round 1 | DatabaseManager.InitializeDatabase() created the Slips table without IsPrinted or CreatedAt columns, but LoadSavedSlipsToDashboard, MarkSlipAsPrinted, and SlipsHistoryForm all query against both columns. | 1. Launch application 2. Observe Main Page load attempt 3. Observe SQL exception thrown | Main Page loads unprinted slip tiles without error | SQL exception thrown on every Main Page load, every 'mark as printed' action, and every History screen open | Migrated to Status (TEXT) + CreatedAt (TEXT) schema per technical spec Section 3, replacing the boolean IsPrinted flag (which also could not represent the later-added 'Voided' state) | Fixed | Review Round 1 | Review Round 1
DEF-002 | Print did not require Save first, allowing printed slips with no database record | Create/Edit Slip | Critical | Critical | Code Review | Review Round 1 | CreateSlip.btnPrint_Click called SlipPrintEngine.ExecutePrintJob directly without ever calling SaveSlip. An operator could go New Slip -> fill in -> Print without ever clicking Save first. | 1. Open New Slip 2. Fill in all fields 3. Click Print directly (do not click Save) 4. Check Slips table for a matching row | Slip is persisted to the database before or during the print action; printed slip always has a corresponding row | Slip printed successfully with zero corresponding database row -- defeats the system's core proof-of-record purpose | Print action now guarantees persistence first: if the slip has not yet been saved, it is saved automatically before Print Preview opens | Fixed | Review Round 1 | Review Round 1
DEF-003 | SlipID editable via Slip History Edit tab | Slip History | High | High | Code Review | Review Round 1 | SlipsHistoryForm's Edit tab included SlipID in its list of editable textboxes and wrote it back via UPDATE slips SET SlipID = ... | 1. Open Slip History 2. Select a slip, open Edit tab 3. Attempt to change the SlipID value 4. Save | SlipID field is not editable under any circumstances, per the immutability requirement | SlipID could be changed and saved, breaking the system's tamper-resistant audit guarantee | SlipID removed entirely from the editable field list and set ReadOnly = true at the control level (defense in depth, not just omitted from the save query) | Fixed | Review Round 1 | Review Round 1
DEF-004 | Print Preview screen built but never invoked | Printing | High | High | Code Review | Review Round 1 | PrintSlipPreview.cs existed as a complete form but nothing in the application ever opened it. Both CreateSlip and SlipsHistoryForm called SlipPrintEngine.ExecutePrintJob directly, sending straight to the physical printer. | 1. Create or open a slip 2. Click Print 3. Observe whether a preview screen appears before printing | Print Preview opens first, showing exactly how the slip will print, before any paper is used | Slip printed immediately with zero preview step, contradicting the agreed design | Print action rewired to open Print Preview first; preview uses the same rendering routine as the live print job, guaranteeing zero mismatch between preview and output | Fixed | Review Round 1 | Review Round 1
DEF-005 | BillNumber not protected at the database level | Database Schema | Medium | Medium | Code Review | Review Round 1 | BillNumber was only 'protected' by one form choosing not to expose it as editable in the UI. No database-level constraint existed to prevent an update via any other code path. | 1. Inspect schema for an UPDATE-blocking constraint on BillNumber 2. Attempt a direct UPDATE statement against BillNumber | Database itself rejects any attempt to change BillNumber after it is first set, regardless of which code path attempts it | BillNumber could be altered by any future code path with no database-level safeguard | Added PreventBillNumberChange trigger (BEFORE UPDATE OF BillNumber, RAISE ABORT) so the protection holds even against a future application bug | Fixed | Review Round 1 | Review Round 1
DEF-006 | Truck Reg (Field1) not enforced as required before printing | Validation | High | High | Code Review | Review Round 2 | btnPrint_Click hardcoded a required check for Tons (Field7) but relied only on a dynamic IsRequired flag for Truck Reg (Field1). That flag defaulted to 0 and was never seeded to 1 for Field1, so a blank Truck Reg could pass print validation. | 1. Open New Slip 2. Leave Truck Reg blank, fill in Tons validly 3. Click Print | Print is blocked with a clear message; Truck Reg is required at every lifecycle stage with no exceptions, matching the strictness already applied to Tons | Slip could be printed with a completely blank Truck Reg | Added an explicit hardcoded check for Field1 in btnPrint_Click (mirroring the existing Tons check); seeded and self-healing migration now forces IsRequired=1 for Field1 and Field7 on every startup; Customize Slips checkbox for Field1's Required flag is now locked, matching Field7 | Fixed | Review Round 2 | Review Round 2
DEF-007 | Main Page tile panel did not scroll | Main Page | Medium | Medium | Code Review | Review Round 2 | flpSlips (the FlowLayoutPanel holding unprinted slip tiles) did not have AutoScroll enabled. Tiles beyond the visible panel area were clipped and inaccessible rather than reachable via scrolling. | 1. Create more unprinted slips than fit in the visible panel height 2. Attempt to view/access the tiles beyond the visible area | A scrollbar appears and all tiles remain reachable, regardless of how many are in progress at once | Tiles beyond the visible area were simply clipped off-screen with no way to reach them | Set AutoScroll = true on flpSlips | Fixed | Review Round 2 | Review Round 2
DEF-008 | Saving an existing printer preset recreates the row instead of updating it in place | Printer Settings | Low | Low | Code Review | Review Round 3 | SaveOrUpdatePrinterProfile uses INSERT OR REPLACE, which in SQLite deletes the existing row and inserts a new one with a new internal ProfileID, rather than updating the existing row's columns in place. | 1. Create a printer preset and note its internal ProfileID 2. Edit and re-save the same preset (same ProfileName) 3. Inspect the ProfileID afterward | ProfileID remains stable across edits to the same named preset | ProfileID silently changes on every edit, even though all current lookups are correctly keyed by ProfileName so no visible symptom exists yet | Resolved: SaveOrUpdatePrinterProfile now uses INSERT ... ON CONFLICT(ProfileName) DO UPDATE SET, a true in-place upsert, so the row and its ProfileID survive an edit. The calibration columns are deliberately excluded from the conflict-update clause so editing a preset from Printer Settings does not reset its saved calibration. | Fixed | Review Round 3 | 2026-08-07
DEF-009 | Void reason prompt: label text visually overlapping the textbox | Slip History | Low | Medium | User Acceptance Testing | UAT Round 1 | The dialog requesting a void reason displayed its prompt/label text partially hidden behind the input textbox, making it hard to read what was being asked for. | 1. Open Slip History 2. Select an unprinted or printed slip 3. Choose Void 4. Observe the reason-prompt dialog layout | Prompt text fully visible, clearly separated from the input textbox, with no overlap | Prompt text appeared to be cut off / hidden underneath the textbox | Dialog layout corrected so prompt text sits fully visible above the textbox with proper spacing Re-verified 2026-08-08 by TC-019, TC-020 and TC-021, which exercised the void reason prompt on both an unprinted draft and a printed slip. | Fixed | UAT Round 1 | UAT Round 1
DEF-010 | Customize Slips screen lacked instructions; locked fields gave no explanation | Customize Slips | Low | Medium | User Acceptance Testing | UAT Round 1 | No on-screen guidance explained how the Field Setup grid worked. Separately, clicking the Hidden or Required checkbox for Field1/Field7 correctly did nothing (by design) but gave no indication why, reading as a possible bug to a new user. | 1. Open Customize Slips with no prior knowledge of the screen 2. Attempt to click the Hidden or Required checkbox for Field1 (Truck Reg) or Field7 (Tons) | On-screen instructions explain how to use the grid; locked checkboxes are visually disabled with an explanatory note nearby | No instructions present; locked checkboxes appeared clickable but silently did nothing, with no explanation | Added an instruction label describing how to use the grid; Field1/Field7 Hidden and Required checkboxes now visibly disabled with a note explaining these two fields are always required and always visible Re-verified 2026-08-10 by TC-023, TC-024 and TC-025, which exercised the label cap and the locked Truck Reg and Tons fields on the Customize Slips screen. | Fixed | UAT Round 1 | UAT Round 1
DEF-011 | Slip History grid allowed direct typing that silently discarded changes | Slip History | Low | Medium | User Acceptance Testing | UAT Round 1 | The DataGridView on the History screen allowed cells to be typed into directly. Edits were correctly never saved (by design -- editing happens via the Edit Slip tab only), but this was not visually obvious, leading users to believe they were editing a live slip in the grid. | 1. Open Slip History 2. Click directly into a grid cell and type a new value 3. Observe whether the value persists or is editable at all | Grid cells are not directly editable; row selection still correctly populates the Edit Slip tab below | Grid cells accepted typed input that was silently discarded, confusing users about where editing actually happens | Set dataGridView1.ReadOnly = true; row selection and Edit Slip tab population left fully intact | Fixed | UAT Round 1 | 2026-07-01
DEF-012 | Paper-size-to-millimeter conversion logic duplicated across three files | Printing | Low | Low | Code Review | Review Round 3 | The same paper-size-to-mm lookup table is independently implemented in PrinterSettingsForm, SlipPrintEngine, and FirstTimeSetupForm. All three currently agree, but there is no single source of truth. | 1. Add a new paper size option to one of the three files 2. Compare behavior across all three | A single shared method supplies paper dimensions to all three call sites | Three independent copies of the same lookup table exist; a future edit to only one risks silent drift between them | Resolved: created PaperSizeHelper.cs as the single source of truth, exposing GetDimensionsMm(profile, slipLengthIn) plus the shared ProfileNames list. PrinterSettingsForm, SlipPrintEngine and FirstTimeSetupForm all call it; the three duplicate switch statements and the duplicated dropdown lists are gone. Unknown profiles now fall back consistently to the 240mm custom roll rather than to A4. | Fixed | Review Round 3 | 2026-08-07
DEF-013 | Void reason input had no character limit — unlimited text could reach the database | Slip Voiding | Low | Medium | User Acceptance Testing | UAT Round 1 | The void reason dialog textbox had no MaxLength set (previously changed to 200), allowing the user to type more than 20 characters. The database methods VoidSlip and VoidPrintedSlip also had no length enforcement, so any string of unlimited length could be written to the VoidReason column. | 1. Open Create or History form 2. Trigger void on a slip 3. In the reason dialog, type more than 20 characters 4. Click Void Slip 5. Check VoidReason value in database | Void reason is capped at 20 characters in both the UI and the database layer | User could type unlimited characters; the full string was written to the database with no truncation | Set MaxLength=20 on void reason TextBox in both CreateSlip and SlipsHistoryForm dialogs. Added hard truncation (Substring 0-20) to VoidSlip and VoidPrintedSlip in DatabaseManager before the SQL write. Referenced TC-20. | Fixed | 2026-07-01 | 2026-07-01
DEF-014 | SlipID field missing from SlipsHistoryForm Edit tab after over-correction for DEF-003 | Slip History | Low | Medium | User Acceptance Testing | UAT Round 1 | The DEF-003 fix removed SlipID from the Edit tab entirely. Users had no reference to which slip they were editing. The field should be visible but read-only — it is never persisted on Save (only Field1-Field10 are written). | 1. Open Slip History 2. Select any slip 3. Switch to Edit tab 4. Note SlipID is absent | SlipID visible as a read-only greyed textbox for reference, matching CreateSlip txtSlipID.ReadOnly = true | SlipID was absent from the Edit tab giving users no reference to the slip being edited | Re-added SlipID textbox to Edit tab with ReadOnly = true, populated on row selection. DEF-003 Save protection intact. Referenced TC-012. | Fixed | 2026-07-01 | 2026-07-01
DEF-015 | Void reason dialog closed silently when reason left blank — no warning shown to user | Slip Voiding | Medium | High | User Acceptance Testing | UAT Round 1 | On both CreateSlip and SlipsHistoryForm, clicking Void Slip with an empty reason field silently dismissed the dialog and returned the user to the form with no message and no void executed. | 1. Select a slip to void 2. Click Void 3. Leave reason blank 4. Click Void Slip 5. Observe dialog closes with no message | Dialog stays open and shows: 'A void reason is required. Please enter a reason before continuing, or click Cancel to abort.' Focus returns to reason textbox. | Dialog closed silently; user returned to form with no feedback that the void was not processed | Replaced DialogResult.OK on button with inline Click handler. Empty reason triggers warning MessageBox and keeps dialog open. Applied to both CreateSlip and SlipsHistoryForm. Referenced TC-19. | Fixed | 2026-07-01 | 2026-07-01
DEF-016 | Field1 and Field7 checkboxes not greyed out on Slip Design tab — appeared editable despite being locked | Customize Slips | Low | Medium | User Acceptance Testing | UAT Round 1 | In the Slip Design tab of CustomizeSlipsForm, the checkboxes for Field1 (Truck Reg) and Field7 (Tons/Weight) were visually identical to editable fields. Although changes were blocked via ItemCheck handlers, the controls gave no visual indication that these fields are locked system fields. | 1. Open Customize Slips 2. Go to Slip Design tab 3. Observe Field1 and Field7 checkboxes in both lists 4. Note they look identical to other checkboxes | Field1 and Field7 checkboxes appear greyed out (disabled) in both the 'fields that print' and 'required fields' lists, clearly indicating they cannot be changed. | Field1 and Field7 checkboxes looked identical to all other fields — no visual cue that they were locked. Users could click them, triggering a blocking message after the fact. | Replaced both CheckedListBox controls with Panel containers holding individual CheckBox controls. Field1 and Field7 set to Enabled = false, rendering natively greyed out. Removed old ItemCheck lock-and-revert logic. Referenced TC-24. | Fixed | 2026-07-01 | 2026-07-01
DEF-017 | Print Preview rendered at a different font scale than the actual print job | Printing | High | High | Code Review | Review Round 4 | PrintSlipPreview.RebuildSlipBitmap read the slip font scale from GlobalSettings['SlipFontScale'], a key that stopped being written when calibration moved into the PrinterProfiles table (commit d64b740, 3 July). Existing databases still hold the orphaned pre-refactor value, so the preview kept rendering at the old scale while SlipPrintEngine.BuildPrintDocument used the active profile's. The preview also never applied the profile's SlipOffsetXMm/SlipOffsetYMm content offsets, which the print path does apply in RenderSlipFromDimensions. | 1. Open Printer Settings and calibrate a preset to a font scale different from the value stored in GlobalSettings (e.g. profile 1.95 vs orphaned 2.75) 2. Save the calibration 3. Open any slip and click Print to open Print Preview 4. Compare the preview rendering against the Calibrate Print screen for the same slip | Print Preview renders the slip identically to the print job and to the calibration screen, per Technical Specification Section 7 which requires preview and print to share one rendering path | Preview rendered the slip at the stale global scale (2.75) while the printer used the profile scale (1.95) -- a 41% size difference -- and ignored the -1mm X offset entirely, so the preview could not be trusted to show what would actually print | PrintSlipPreview now reads SlipFontScale from the active PrinterProfile, the same source BuildPrintDocument uses, and applies SlipOffsetXMm/SlipOffsetYMm when drawing the slip bitmap. Verified 2026-08-07: Print Preview and Calibrate Print render the same slip at identical proportions. | Fixed | 2026-08-07 | 2026-08-07
DEF-018 | Automatic backup retention could delete a backup moments after creating it | Backup | High | Medium | Code Review | Review Round 4 | PerformStartupBackup creates each backup with File.Copy, which carries the SOURCE file's last-write timestamp onto the copy. The rolling 30-day purge immediately below then evaluates that inherited timestamp, so it measures the age of the DATA rather than the age of the BACKUP. Once the database goes 30 days without a write, every new backup is born already expired and is deleted on the next launch. | 1. Note the database file's last-modified date 2. Launch the application to trigger the startup backup 3. Inspect the new file in the Backups folder and compare its Date Modified against its filename timestamp | Each backup file carries the date and time the backup was actually taken, so the 30-day rolling window retains recent backups and prunes genuinely old ones | Backup files carried the database's last-modified date instead. Observed in the wild: WeighbridgeData_20260807_113332.db was created at 11:33 on 7 August but stamped 5 August, and WeighbridgeData_20260805_080052.db was stamped 14 July. | Added File.SetLastWriteTime(backupFile, DateTime.Now) immediately after the File.Copy in PerformStartupBackup, so the purge measures backup age. Verified 2026-08-07: WeighbridgeData_20260807_123507.db carries a matching 7 August 12:35 timestamp. Referenced TC-039. | Fixed | 2026-08-07 | 2026-08-07
DEF-019 | Slip History grid displayed a phantom empty row beneath the results | Slip History | Low | Medium | User Acceptance Testing | UAT Round 2 | dataGridView1.ReadOnly was correctly set to true by the DEF-011 fix, but AllowUserToAddRows was never disabled. The grid therefore still rendered the DataGridView new-row placeholder -- an empty row marked with an asterisk -- below the real results, in both the Printed and Voided views. | 1. Open Slip History 2. Observe the row immediately below the last real result 3. Repeat with a date range that returns no results at all | The grid shows only rows that correspond to real slips; an empty result set shows an empty grid | An empty placeholder row appeared under the results, and appeared as the only row when the filter returned nothing -- reading as a slip record that does not exist, directly beneath a 'Total Slips: 0' summary | Set AllowUserToAddRows = false and AllowUserToDeleteRows = false on the history grid. Verified 2026-08-07 in both Printed and Voided views. | Fixed | 2026-08-07 | 2026-08-07
DEF-020 | Excel export dropped hidden fields, so column structure varied between exports | Excel Export | Medium | Medium | Code Review | Review Round 4 | ExportToXlsx built its column list from the DataGridView's visible columns, so a field marked Hidden in Customize Slips lost its column from the exported file entirely. Technical Specification Section 8 states the opposite -- that all ten Field columns must appear even when hidden, because 'hidden' means 'does not print on the physical slip', not 'excluded from the data record'. Test case TC-035 had been written to assert the incorrect behaviour. | 1. Hide any field via Customize Slips (e.g. Field2) 2. Export from Slip History 3. Inspect the exported column headers 4. Unhide the field, export again, and compare the two files' column structure | Every export has an identical column structure regardless of which fields are currently hidden, so exported files remain comparable to one another over time | The hidden field's column vanished from the export, so two exports taken either side of a visibility change had different shapes and could not be compared or appended | Export now always writes a fixed 17-column structure: Slip ID, Bill Number, Status, Created At, Printed At, all ten Field columns under their current labels, Voided At, and Void Reason. A hidden field keeps its column and exports blank (stakeholder decision, 7 August: retain the column for database consistency, blank the value). Rows still follow the active date range and filters. Verified 2026-08-07: with Field9 (Slot) hidden, the Slot column was present and empty. TC-035 rewritten to match. | Fixed | 2026-08-07 | 2026-08-07
DEF-021 | Orphaned calibration keys left behind in GlobalSettings after the PrinterProfiles refactor | Database Schema | Low | Low | Code Review | Review Round 4 | When per-preset calibration moved from GlobalSettings into the PrinterProfiles table (commit d64b740, 3 July), the old GlobalSettings rows were never removed. SlipFontScale, SlipOffsetXMm and SlipOffsetYMm still exist in every pre-existing database holding their last pre-refactor values. After the DEF-017 fix nothing reads or writes them, so they are inert -- but they look authoritative and contradict the live values in PrinterProfiles. | 1. Open the WeighbridgeData.db file in any SQLite browser 2. Inspect the GlobalSettings table 3. Compare SlipFontScale there against SlipFontScale on the active row of PrinterProfiles | GlobalSettings contains only keys the application actually reads; superseded calibration keys are removed by the same migration that introduced their replacements | GlobalSettings still reports SlipFontScale = 2.75, SlipOffsetXMm = 0 and SlipOffsetYMm = -1.5 while the active profile holds 1.95, -1 and 0. Anyone inspecting the database would read the wrong values as current. No runtime symptom. | Fixed 2026-08-11. A DELETE for the three superseded keys now sits in MigrateSchemaIfNeeded directly beneath the ALTER statements that added the replacement columns, which is where the 3 July migration should have put it. The keys are named explicitly rather than swept by a whitelist of live settings: an unrecognised key is far likelier to be one added after this code was written than one this refactor stranded, and deleting that would be the worse mistake. An audit of every GetGlobalSetting and SaveGlobalSetting call site confirmed these three were the only orphans; the other nine keys are all read or written by current code. Verified in a running build against the archived 7 August database, which held SlipFontScale 2.75, SlipOffsetXMm 0 and SlipOffsetYMm -1.5 against a live profile of 1.95, -1 and 0: after launch the three rows are gone, Print Calibration still reads 1.95, -1.0 and 0.0, and all 16 slips, 16 bill numbers, 3 printer profiles and 10 field labels are unchanged. Referenced TC-053. | Fixed | 2026-08-07 | 2026-08-11
DEF-022 | Editing a saved draft and clicking Print discarded the edits from the database | Create/Edit Slip | Critical | High | Code Review | Review Round 5 | CreateSlip.btnPrint_Click only wrote to the database when ExistingSlipId was 0. Re-opening an already-saved draft from its Main Page tile, changing a value and clicking Print sent the NEW values to the printer while the row kept its OLD values, then marked the slip Printed. Same class of failure as DEF-002: the printed record and the stored record disagreed. | 1. Create and Save a slip so it appears as a Main Page tile 2. Click the tile to re-open the draft 3. Change any value (e.g. Tons) 4. Click Print WITHOUT clicking Save first 5. Confirm the print, then inspect the row in Slip History | Print always persists the current on-screen values before printing, so the printed slip and its database row are identical | The paper carried the edited values while the database retained the values from the last Save, and the slip was marked Printed in that stale state -- defeating the proof-of-record purpose | Added the missing else-branch to btnPrint_Click calling UpdateSlipFields for an existing draft before the preview opens. Referenced TC-041. | Fixed | 2026-08-07 | 2026-08-07
DEF-023 | First-Time Setup silently discarded the chosen paper size when 'save as preset' was unticked | First-Time Setup | High | High | Code Review | Review Round 5 | The printer profile was only written when chkSavePreset was ticked. Unticked, the seeded Default profile remained -- hardcoded to Small240x102 (240 x 139.7 mm) and marked IsActive. Since SlipPrintEngine.GetPageDimensionsMm reads the active profile ahead of GlobalSettings, the operator's paper choice was ignored entirely. | 1. Delete WeighbridgeData.db so First-Time Setup runs 2. Select a paper size other than Small240x102, e.g. A4 3. UNTICK 'Save as printer preset named' 4. Click Get Started 5. Open Printer Settings and inspect the active preset | The active preset always reflects the paper size chosen during setup; the checkbox decides which profile receives the values, never whether they are kept | The active profile stayed at Small240x102 240 x 139.7 mm regardless of the selection -- the same silently-wrong paper size class of fault the project exists to eliminate | Setup now always calls SaveOrUpdatePrinterProfile; the checkbox only selects the target profile name (a named preset, or the seeded Default). Verified 2026-08-07: choosing A4 with the box unticked produced Default ¦ A4 ¦ 210 x 297. Referenced TC-044. | Fixed | 2026-08-07 | 2026-08-07
DEF-024 | Slip History date filter used the creation date for every status | Slip History | Medium | Medium | Code Review | Review Round 5 | QuerySlips and GetDistinctFieldValues filtered on CreatedAt regardless of the status being viewed, but a slip's dates diverge -- one created on the 1st can be printed on the 2nd. A 'printed on this date' search therefore missed slips created earlier. Voided slips were worse: no VoidedAt column existed at all, so a void could only ever be filtered by creation date. | 1. Find a printed slip whose Created At and Printed At fall on different days 2. Set the History date range to the PRINTED day only 3. Observe whether the slip appears | Printed slips filter on Printed At, voided slips on Voided At, drafts on Created At -- each status filtered by the date its own event actually happened | The slip was absent. Live example: slip 10 was created 2026-07-01 and printed 2026-07-02, and a 2 July filter did not return it. | Added a VoidedAt column with a migration that backfills existing voided rows from CreatedAt, set it on both void paths, and routed both queries through a DateColumnFor(status) helper so the grid and its filter dropdowns always agree. Voided At is shown in the Voided view and included in the export. Verified against live data: the 2 July filter now returns slips 10 and 11. Referenced TC-045. | Fixed | 2026-08-07 | 2026-08-07
DEF-025 | Tons format was not re-checked at print time, so a pasted value could bypass validation | Validation | Low | Medium | Code Review | Review Round 5 | txtField7_KeyPress filters typed characters, but paste does not raise KeyPress and btnSave_Click never validated the format. A value such as 12.5.3 could therefore reach the database on a draft. Print was blocked in practice only because ValidatePrintButton disables the button -- btnPrint_Click itself performed no format check, which Technical Specification Section 4.4 explicitly requires as a stale-UI-state guard. | 1. Open a slip and paste an invalid value such as 12.5.3 into Tons 2. Click Save 3. Re-open the draft and attempt to Print | An unparseable tonnage can never reach the printer, whatever the state of the Print button | No explicit format check existed on the print path; the protection relied entirely on the button's enabled state | Added a double.TryParse guard to btnPrint_Click, after the blank check, showing a clear message and blocking the print. Scope agreed with the project owner as print-time only, so a partially typed value can still be saved as a draft. | Fixed | 2026-08-07 | 2026-08-07
DEF-026 | Database timestamps were stored in UTC while every other timestamp used the machine clock | Database Schema | Medium | High | Code Review | Review Round 5 | CreatedAt, PrintedAt and VoidedAt were written with SQLite datetime('now'), which always returns UTC. BillNumber, the date printed on the slip, and the backup and export filenames all come from C# DateTime.Now, which is machine-local. On a UTC+2 machine every database timestamp sat two hours behind everything the operator could see, and the History date filter compared locally-picked dates against UTC columns -- putting two hours of every day on the wrong side of the range. | 1. Note the PC clock 2. Create and print a slip 3. Compare its Bill Number and the date on the paper against Created At and Printed At in the grid | Every timestamp uses the clock of whatever machine the application runs on, so all four sources agree | Bill Number and the printed date read local time while Created At and Printed At read UTC -- a constant two-hour discrepancy on this machine, and a different one on any machine in another zone | All timestamp writes changed to datetime('now','localtime'), including the CreatedAt column default. InsertSlip now sets CreatedAt explicitly so databases created before this change are also corrected without rebuilding the table. GetDailySummary and GetDailyTonsByField had their 'localtime' conversions removed, since converting an already-local value would have shifted it a second time. Verified on a fresh database: Bill Number 20260807-162406, CreatedAt 16:25:41, PrintedAt 16:27:21, all machine-local. Referenced TC-043. | Fixed | 2026-08-07 | 2026-08-07
DEF-027 | Reprinted slips were stamped with the current date instead of the original print date | Printing | Medium | High | Code Review | Review Round 5 | RenderSlipContent read a CreatedAt key from the print package, but neither the first-print path nor the reprint path ever supplied one, so the line always fell through to DateTime.Now. Every sheet was stamped with the moment it left the printer under a label reading 'Printed:'. Two reprints of one slip carried two different dates and neither matched the database. | 1. Note a printed slip's Printed At value in Slip History 2. Select it and click Print 3. Read the date shown on the preview | Every copy of a slip shows the date it was FIRST printed, matching the database row, since a reprint is a copy of the same record rather than a new event | The preview showed the current date. Live example: slip 11, printed 2026-07-02 13:40, previewed on 2026-08-07 and stamped 'Printed: 2026-08-07 12:37'. | SlipsHistoryForm now passes the slip's stored PrintedAt into the print package and RenderSlipContent prefers it over the current time, falling back only for a slip being printed for the very first time. MarkSlipAsPrinted additionally wraps PrintedAt in COALESCE so the first-print date can never be overwritten by any code path. Verified 2026-08-07: reprinting slip 11 left PrintedAt at 2026-07-02 13:40:58 unchanged. Referenced TC-042. | Fixed | 2026-08-07 | 2026-08-07
DEF-028 | First-Time Setup created the database before Get Started, so abandoning setup left a half-configured system | First-Time Setup | High | Medium | User Acceptance Testing | UAT Round 2 | BtnCustomizeFields_Click calls DatabaseManager.InitializeDatabase() so CustomizeSlipsForm can load the field list. That write committed the database before the operator had finished. Program.cs decides whether to show setup purely on whether the file exists, so closing the setup screen after using Customize Fields left a database holding seeded defaults -- the Small240x102 profile, the default company name, and none of the operator's selections -- and every later launch skipped setup entirely, with no route back to it short of deleting the file by hand. | 1. Delete WeighbridgeData.db so First-Time Setup appears 2. Click 'Customize Fields...' and close that window 3. Close the setup screen with the X, WITHOUT clicking Get Started 4. Relaunch the application | Only Get Started commits a setup. Abandoning the screen leaves no database behind, and the next launch shows First-Time Setup again. | The next launch opened straight onto the Main Page against a database the operator never completed -- wrong paper size, wrong company name, and no way to re-run setup | FirstTimeSetupForm now tracks whether it created the database and deletes it again in OnFormClosing when the dialog result is anything other than OK. Added DatabaseManager.DeleteDatabaseFile(), which clears the SQLite connection pool first so the handle is released before the delete. Verified 2026-08-08: after Customize Fields and an X-close, the relaunch showed setup again. Referenced TC-046. | Fixed | 2026-08-08 | 2026-08-08
DEF-029 | Slip Length accepted letters; invalid input was only rejected on Get Started | First-Time Setup | Low | Medium | User Acceptance Testing | UAT Round 2 | The Slip Length textbox applied no input filtering, so any text could be typed into a field that only ever holds a measurement in inches. The value was validated on Get Started, but during testing the tester could not tell whether the entry had actually been blocked -- the rejection was not evident at the point of entry, unlike the Tons field which filters keystrokes as they are typed. | 1. Open First-Time Setup 2. Set Paper Size to Small240x102 so the Slip Length field appears 3. Type 'abc' into Slip Length | Letters cannot be entered at all, consistent with the Tons field. Blank or incomplete values are still caught by the Get Started validation as a backstop. | Letters could be typed freely, and whether they had been rejected was not apparent from the screen | Added a KeyPress filter to Slip Length allowing digits and at most one decimal separator, plus MaxLength 6, mirroring txtField7_KeyPress on CreateSlip. The Get Started validation is retained for blank or pasted values. Verified 2026-08-08: 'abc' produced no input, '5.5' was accepted, a second separator was refused. TC-003 rewritten to assert prevention rather than a message. | Fixed | 2026-08-08 | 2026-08-08
DEF-030 | Renaming a field does not move its lookup list, and there is no way to reassign one | Customize Slips | Medium | Medium | User Acceptance Testing | UAT Round 2 | FieldConfig.LookupTable is assigned per field slot when the database is first created and is never changed again. Customize Slips lets the operator rename a field but offers no way to change which lookup list feeds that field's dropdown, so after a rename the field suggests values from the wrong domain. The effect compounds: SaveLookupValue writes any newly typed value into whichever table the slot is bound to, so continued use progressively mixes unrelated values into both lists. | 1. Open Customize Slips and rename Field6 from 'Destination' to 'Slot number' 2. Rename Field9 from 'Slot' to 'Destination' 3. Save 4. Open Create Slip and drop down each of those two fields | A field's dropdown suggests values appropriate to its current label, or the operator has some way to reassign which lookup list feeds it. | Field6, labelled 'Slot number', suggested destination names from the Destinations table, while Field9, labelled 'Destination', suggested slot codes from the Slots table. Any new value typed into either was saved back into the mismatched table. | Suggestion lists no longer belong to a field slot. The nine fixed tables and FieldConfig.LookupTable are gone, replaced by LookupLists / LookupEntries keyed on the field's label, matched case-insensitively and ignoring a trailing colon. A list is created the first time a value is saved under a label, so a rename to an unused name starts empty and a rename back to a previous name restores that list intact. Values are captured when the slip is written rather than on leaving the box, so an abandoned form no longer feeds the list. Manage Lookups now lists every list including ones no field points at, and can clear or delete them. Existing lookup values are dropped on upgrade by decision of the project owner, since the lists rebuild from use. Side effect: the list name is now a bound parameter rather than an interpolated table name, so the lookup queries are no longer built by string concatenation. Referenced TC-049 to TC-052. | Fixed | 2026-08-10 | 2026-08-11
DEF-031 | Main Page tiles kept their old headings after a field was renamed | Main Page | Medium | Medium | User Acceptance Testing | UAT Round 3 | BuildTileText resolves each tile heading from FieldConfig every time it runs, so a tile built after a rename is always correct. The problem was that nothing rebuilt the existing tiles: btnCustomizeSlips_Click opened Customize Slips and did nothing with the result, so the dashboard on screen kept the headings it was drawn with. Opening Tile Display and re-saving the same selection did force a redraw, which is why re-picking the field looked like the cure -- it was rebuilding the tiles, not repairing any stored caption. | 1. On the Main Page open Tile Display, choose a field such as Field10 and Save 2. Confirm the tiles show that field's current heading 3. Open Customize Slips, rename that field and Save 4. Return to the Main Page without touching Tile Display | The tiles carry the new heading as soon as the rename is saved, with no second step | The tiles kept the previous heading. The operator had to reopen Tile Display and re-select the same field before the dashboard caught up. | btnCustomizeSlips_Click now reloads the dashboard, the empty state and the daily summary when Customize Slips closes with DialogResult.OK, and the Tile Display button already did the same. Verified 2026-08-11: renaming Field10 from 'Compony' to 'Client' left the tiles reading 'Client: RGN-ORE' with no further action. Referenced TC-047. | Fixed | 2026-08-11 | 2026-08-11
DEF-032 | Renaming a field gave no warning of how far the change reached | Customize Slips | Low | Medium | User Acceptance Testing | UAT Round 3 | Customize Slips committed a new label silently. A field label is used by the Create Slip form, the Slip History grid and its filter dropdowns, the View and Edit tabs, the printed slip, the Excel export headings, the Main Page tiles, the daily summary breakdown and the Manage Lookups selector -- so a rename has a reach the operator could not see before committing to it. Two consequences are especially easy to get wrong: already-recorded slips do not change, because a slip stores the value rather than the label; and the lookup list feeding that field's dropdown does not follow the rename, which is the open DEF-030 behaviour. | 1. Open Customize Slips from the Main Page 2. Change the label of any field 3. Click Save | Before the rename is committed the operator is shown exactly which labels are changing and everywhere the new wording will appear, with the option to cancel | The rename was written straight to FieldConfig with no summary and no confirmation step | CustomizeSlipsForm.btnSave_Click now builds a 'Renaming Fields' confirmation listing each changed label as old to new, enumerating every surface the new wording will appear on, and stating that recorded slips are unaffected and that dropdown suggestions do not follow the rename. OK commits, Cancel abandons. Verified 2026-08-11 on Field10: 'Compony' to 'Client'. Referenced TC-048. | Fixed | 2026-08-11 | 2026-08-11
DEF-033 | Copies on one page were locked to a single arrangement | Printing | Low | Medium | Customer Acceptance Testing | Customer Testing Round 1 | RenderSlipForPreview decided the arrangement itself: two copies always as two columns split by a vertical cut line, four always as a 2x2 grid. Which way the copies sit decides which way the page is torn or guillotined, and that follows from the customer's paper and how they handle it rather than from anything the software can know. No setting exposed the choice. | 1. Open Printer Settings and click Calibration Page 2. Set Copies to 2 3. Look at the preview, then click Print Test Page 4. Repeat with Copies set to 4 | The operator chooses whether copies sit side by side or stacked, and the printed sheet matches the preview exactly | Two copies always printed side by side and four always as a 2x2 grid. There was no way to change it. | Added an Arrangement setting beside Copies offering Side by side, Stacked, and Grid (2 x 2), the last only when 4 copies is selected since for two it would behave as side by side. Stored per preset in a new PrinterProfiles.MultiSlipLayout column defaulting to 'Columns', so an existing preset prints exactly as it did before. The tiling decision moved into SlipPrintEngine.GetTiling, which the print path, the calibration preview and the preview's bitmap sizing all call, so the paper can never disagree with the screen. The preview bitmap is now built at the cell's real proportions, so a stacked copy is laid out wide and short rather than drawn tall and squashed. Referenced TC-054. | Fixed | 2026-08-13 | 2026-08-13
DEF-034 | Printing to PDF opened a Save dialog with no file name filled in | Printing | Low | High | Customer Acceptance Testing | Customer Testing Round 1 | The Save Print Output As dialog raised by Microsoft Print to PDF opened with an empty File name box, so the operator had to invent and type a name for every slip. PrintDocument.DocumentName was never set. Setting it alone does not fix this: it renames the print job, which is why the name appears in the Printing progress window, while the driver's own Save dialog ignores it entirely. | 1. Choose Microsoft Print to PDF as the printer 2. Create a slip and click Print, then confirm the preview 3. Look at the File name box in the Save dialog | The Save dialog opens with a sensible name already in it, still editable, so a folder of saved slips can be read at a glance | The File name box was empty on every slip. | The application now raises its own SaveFileDialog, pre-filled with the bill number and the leading visible field's value (for example '20260812-091335 - LFN550NW'), and hands the chosen path to the driver through PrintToFile and PrintFileName. Given a path the driver writes straight to it and does not prompt again, so the operator still sees exactly one dialog. The leading field follows the operator's own field order rather than being fixed to Field1, characters Windows rejects in a file name are stripped, and the folder last saved into is remembered. Verified 2026-08-13. Referenced TC-055. | Fixed | 2026-08-13 | 2026-08-13
DEF-035 | Cancelling the PDF Save dialog marked the slip Printed with no document produced | Slip Lifecycle | Critical | Critical | Code Review | Customer Testing Round 1 | PrintDocument.Print() returns normally when the operator cancels the printer driver's own Save dialog - the driver discards the job rather than raising an error. PrintSlipPreview.BtnPrint_Click set DialogResult.OK as soon as Print() returned, and CreateSlip marks the slip Printed on that result. Cancelling therefore recorded a printed slip with no document anywhere, and a printed slip can never be un-printed. Found while fixing DEF-034. It can only occur on the print-to-file path, which is why 53 passing test cases had never reached it. | 1. Choose Microsoft Print to PDF as the printer 2. Create a slip and click Print, then confirm the preview 3. Click Cancel on the Save dialog 4. Find the slip in Slip History and check its status | A cancelled print leaves the slip an unprinted draft on the Main Page, since nothing was produced | The slip was marked Printed although no PDF was written, and being printed it could then only be voided, never returned to draft | The Save dialog is now the application's own, and its result is checked before anything is printed. Cancelling returns without printing and without setting DialogResult.OK, so the slip stays a draft. Verified 2026-08-17: cancelling the Save dialog left the slip's tile on the Main Page and it did not appear among the printed slips. Referenced TC-056. | Fixed | 2026-08-13 | 2026-08-17
DEF-036 | The company logo was stored as a file path, so it could not travel with the system | Printing | High | High | Code Review | Customer Testing Round 1 | GlobalSettings.LogoPath held an absolute path to a picture elsewhere on the machine. Handing the application to anyone else broke it immediately since that path does not exist on their PC, and the customer moving or deleting their own file broke it just as easily. The draw was guarded by File.Exists and wrapped in an empty catch, so a missing or unreadable picture printed a slip with no letterhead and reported nothing at all. | 1. Set a logo from a file in Customize Slips 2. Move, rename or delete that file - or copy the application to another machine 3. Print a slip | A configured logo prints wherever the application runs and whatever happens to the original file, and a logo that cannot be loaded is reported rather than silently dropped | The slip printed with no logo and no message. Nothing indicated the letterhead was missing. | The image is stored in the database, so it travels with the file, is captured by every backup, and cannot be broken by moving or deleting anything. A stored logo that will not decode now reports the failure instead of quietly omitting the letterhead. The old LogoPath is read once during migration and the picture pulled in if it still resolves, so a logo configured before this change survives the upgrade rather than being lost. Verified 2026-08-13. Referenced TC-057. | Fixed | 2026-08-13 | 2026-08-13
DEF-037 | Company Name and Slip Length boxes overlapped on the Printer Settings screen | Printer Settings | Low | Low | User Acceptance Testing | Customer Testing Round 1 | The two right-column rows were positioned 15px apart while the text boxes are 22px tall, so they overlapped by 7px and rendered as one tall control holding two lines of text. The margin rows below already used a 38px pitch; only this pair was wrong. Both boxes also ran past the form's right edge once Windows scaled the form up on a high-DPI display, since the form is AutoScaleMode.Font and a control that clears the edge at design size need not clear it once scaled. | 1. Open Printer Settings 2. Look at the Company Name and Slip Length fields | Each field has its own clearly separated box, and both sit well inside the form at any display scaling | The two boxes overlapped and read as a single control with two lines of text in it, and both ran to the form's right edge | The right column now uses one running row pitch matching the margins below it, so the pair cannot drift into each other again and a row added later needs no hand-adjusted coordinates. Control width dropped from 230 to 190 and the form's client width went from 950 to 1020. Verified 2026-08-13. Referenced TC-058. | Fixed | 2026-08-13 | 2026-08-13
DEF-038 | Landscape rotated the paper but not the layout, so the lower part of the page printed off the sheet | Printing | High | High | User Acceptance Testing | Customer Testing Round 1 | PageSettings.Landscape was set, so the driver duly turned an A4 sheet to 297 x 210. The renderer, however, kept laying content out for the profile's stored 210 x 297. It therefore arranged a 190 x 277 mm column of content and sent it to a sheet only 190 mm tall. Everything below that line fell off the paper. With two copies on a page the first slip printed and the second ran off the bottom. The same disagreement reached both preview canvases, which drew a portrait page while the printer produced a landscape one. | 1. Printer Settings: set Orientation to Landscape on the active preset and save 2. Set Copies per page to 2 on the calibration screen 3. Print a slip, to paper or to PDF 4. Compare what came out against the preview | The sheet prints landscape and the content is laid out for the landscape shape, with both previews showing the same page the printer produces | The page rotated but the content did not: the first slip printed and the second was cut off by the bottom edge of the sheet. Both previews showed a portrait page throughout. | Split the two ideas of the page apart. GetPaperStockMm returns the stock's own unrotated size and is what the driver's PaperSize receives, alongside the Landscape flag that actually performs the rotation. GetPageDimensionsMm returns that swapped, and is what everything that draws uses -- the renderer, both preview canvases and the multi-copy cell maths. Also corrected an interim attempt that expressed landscape purely as a swapped PaperSize with no rotation flag: the driver ignores a custom size on its own and silently prints portrait, so the previews turned landscape while the paper did not. Verified 2026-08-17 against PDF output in both orientations. Referenced TC-059. | Fixed | 2026-08-17 | 2026-08-17
DEF-039 | Backups could not be restored from inside the application | Backup | High | High | Code Review | Review Round 6 | PerformStartupBackup and PerformManualBackup wrote copies; nothing ever read one back. The word 'restore' did not appear anywhere in the codebase. Recovering from a damaged database meant closing the program, finding %ProgramData%\UitvalSlips by hand, renaming files, and knowing to delete stray -journal files first. On a system whose purpose is holding the permanent record of what left the yard, a backup the operator cannot actually use is half a feature, and the missing half is the one needed on a bad morning. | 1. Note that copies exist in the Backups folder 2. Open the application and look for any way to put one back 3. Search the source for a restore path | The operator can choose a backup and put it back from inside the program, without file surgery and without telephoning the developer. | No restore existed. The only route was manual file manipulation in a hidden system folder. | Added a Restore screen listing every backup with its age and the slip counts read from the file itself, so the operator can see what each copy holds before choosing. A copy that will not open is shown in red and cannot be selected. The restore validates the chosen backup before touching anything, moves the current database aside as WeighbridgeData_replaced_<timestamp>.db rather than deleting it, puts the original back if the copy fails, clears pooled SQLite handles so the file is not locked, and removes stray -journal and -wal files belonging to the replaced database which SQLite would otherwise try to apply to the restored one. Referenced TC-060 and TC-061. | Fixed | 2026-08-18 | 2026-08-18
DEF-040 | Automatic backups were taken only at launch, so a fault mid-day cost the whole day | Backup | High | High | Code Review | Review Round 6 | PerformStartupBackup was called once from Program.Main and was the only automatic backup in the system. An operator starting at 06:00 and working until 16:00 therefore had exactly one copy, taken at 06:00. Any database fault during the day rolled the records back ten hours, and every slip issued in between would have existed only on paper. | 1. Start the application 2. Enter and print several slips over the course of a day 3. Inspect the Backups folder for any copy taken after startup | Backups follow the work being done, so a database fault costs minutes rather than a day. | One backup per launch, and nothing after it however many slips were entered. | Backups now follow each committed change -- a draft saved, a slip printed, edited or voided -- throttled to at most one every fifteen minutes so a busy morning does not fill the disk with near-identical copies. Startup still forces one regardless of the interval. Retention changed to match: every copy from the last three days, then the first copy of each day out to thirty, since the previous flat thirty-day rule combined with quarter-hourly backups would have left several hundred files. Referenced TC-062. | Fixed | 2026-08-18 | 2026-08-18
DEF-041 | The licence check refused the very computer its licence was issued for | Licensing | Critical | Critical | User Acceptance Testing | UAT Round 4 | MachineFingerprint.Components returns the full 64-character SHA-256 of each of the three hardware identifiers. A machine code carries only the first ten characters of each, which is therefore all ParseMachineCode can hand back. Compare tested the full sixty-four against those ten and so could never report a match on any machine, under any circumstances. The signature check was sound, so a licence verified as genuine and was then rejected as belonging to a different computer -- while the screen displayed the licensed code and the machine code as identical strings. | 1. Read the machine code from the licence screen 2. Issue a licence for exactly that code 3. Paste it in and click Activate 4. Compare the two codes shown in the refusal message | A licence issued for this computer activates on this computer. | Refused with 'genuine but issued for a different computer', quoting a licensed code and a machine code that were character-for-character the same. Every install would have failed this way on first use. | Both sides now truncate through a single Prefix helper, so the ten-character length is defined once rather than being set in MachineCode and separately assumed in Compare. Verified 2026-08-19 on the machine that had just refused itself. Referenced TC-063. | Fixed | 2026-08-19 | 2026-08-19

## Summary
Defect Log — Summary
Truck Loading Slip Management System
Total defects logged | 41
Fixed | 41
Open | 0
By severity
Critical | 5
High | 11
Medium | 9
Low | 16
By discovery method
Code Review (static) | 23
User Acceptance Testing (dynamic) | 16
Customer Acceptance Testing (review) | 2
Note: 'Code Review' = defects found through static analysis of source code against the project specification, before runtime testing. 'User Acceptance Testing' = defects found through hands-on, exploratory use of the running application by an end-stage tester. 'Customer Acceptance Testing' = defects raised by the customer while reviewing a pre-release build. All three are pre-deployment: the system has not been used in live operation, and no defect in this log was found during operational use.